## Proper Timeline of the project
Week | Task ID | Category | Task Description | Status (Not Started/In Progress/Done)
Week 1 | W1-T1 | Environment | Install Python 3.8+ and create a virtual environment
| W1-T2 | Environment | Install required libraries: opencv-python face_recognition numpy pandas
| W1-T3 | Database | Design SQLite database with a table 'students' (id name embedding)
| W1-T4 | Database | Write a Python script to create the database and table
| W1-T5 | Registration | Write a script that opens webcam and detects faces using face_recognition
| W1-T6 | Registration | Allow user to enter student name/ID when a face is detected
| W1-T7 | Registration | Capture 10-15 face frames per student and compute embeddings for each
| W1-T8 | Registration | Average the embeddings and store the final vector in the database
| W1-T9 | Testing | Enroll at least 5 test subjects and verify data is stored correctly
Week 2 | W2-T1 | Detection | Write function detect_faces(image) that returns bounding boxes for all faces
| W2-T2 | Detection | Test detection on group photos (download classroom-like images)
| W2-T3 | Recognition | Write function recognize_face(face_encoding) to compare against database
| W2-T4 | Recognition | Compute distance (Euclidean or cosine) and find best match below threshold (start 0.6)
| W2-T5 | Recognition | Test recognition on individual faces and verify correct match
| W2-T6 | Tuning | Experiment with different threshold values to balance false positives/negatives
| W2-T7 | Integration | Combine detect + recognise into a pipeline that processes a whole image
Week 3 | W3-T1 | Attendance | Write function mark_attendance(image) that detects and recognises all faces
| W3-T2 | Attendance | Create a list of recognised student IDs/names (avoid duplicates per session)
| W3-T3 | Database | Create a new table 'attendance' with columns: student_id date status
| W3-T4 | Database | For each recognised student insert a record with status = 'Present'
| W3-T5 | Logic | Add session check â€“ do not mark same student twice on the same day
| W3-T6 | Testing | Test with group images containing known and unknown faces
| W3-T7 | Reporting | Generate a simple summary (e.g. print present/absent list)
Week 4 | W4-T1 | UI Framework | Choose UI framework (Tkinter or Streamlit) and set up the project
| W4-T2 | UI - Home | Design Home screen: options for "Take Attendance" and "Register New Student"
| W4-T3 | UI - Registration | Design Registration screen: webcam feed + input fields for name/ID
| W4-T4 | UI - Registration | Connect the Register button to your registration module
| W4-T5 | UI - Attendance | Design Attendance screen: button to capture/upload image and process it
| W4-T6 | UI - Attendance | Display detected faces with bounding boxes and recognised names on the image
| W4-T7 | UI - Reports | Design Reports screen to view attendance history
| W4-T8 | UI - Export | Add export functionality to download attendance as CSV using pandas
Week 5 | W5-T1 | Enrolment | Enrol 40+ students (use classmates or public face datasets) ensure 10+ images each
| W5-T2 | Testing - Lighting | Test the system under different lighting conditions (bright dim mixed)
| W5-T3 | Testing - Angles | Test with different head poses (frontal slight side looking down)
| W5-T4 | Testing - Scale | Test with images containing 40+ students (simulate classroom)
| W5-T5 | Performance | Measure recognition accuracy (correct / total present)
| W5-T6 | Optimisation | If slow â€“ downscale image for detection or pre-load all embeddings at startup
| W5-T7 | Edge Cases | Handle "Unknown" faces â€“ log them for manual review
| W5-T8 | Edge Cases | Ensure no duplicate marking in a single session
| W5-T9 | Documentation | Write user manual (installation usage troubleshooting)
| W5-T10 | Code Cleanup | Add comments and docstrings to all functions
| W5-T11 | Final Demo | Prepare a live demo or video showing registration â†’ attendance â†’ report export